## Sheet1
| Consequence | [5 empty] | Risk | Statement | Response | Likelihood | Consequence | Risk
Likelihood |  | Negligible 1 | Minor 2 | Moderate 3 | Major 4 | Catastrophic 5 | Internet outage | Internet may cut out | Fix it or wait for it to be fixed | 3 | 1 | 3
| Rare 1 | Low 1 | Low 2 | Low 3 | Moderate 4 | Moderate5 | Computer Damage | Computer could break | Fix it or get a new one | 1 | 2 | 2
| Unlikely 2 | Low 2 | Moderate 4 | Moderate 6 | High 8 | High 10 | Using new software | Using unfamiliar difficulties will bring delays | Spend time learning new software | 5 | 2 | 10
| Possible 3 | Low 3 | Moderate 6 | High 9 | High 12 | Extreme 15 | Poor health | Unforseen health issues | Response unique to each situation | 1 | 4 | 4
| Likely 4 | Moderate 4 | High 8 | High 12 | Extreme 16 | Extreme 20 | Additional requirements | More requirements could be added to the project | Adjust agile methods | 2 | 1 | 2
| Almost Certain 5 | Moderate 5 | High 10 | Extreme 15 | Extreme 20 | Extreme 25 | Time required elsewhere | I may be required to attend training days | Adjust agile methods | 5 | 1 | 5
[7 empty] | Unclear requirements | Initial requirements unclear | Alter goals as project progresses | 3 | 2 | 6
[7 empty] | Help unavailable | Trainers may be too busy to help with issues | Wait or continue trying solutions | 4 | 1 | 4
[7 empty] | Low Motivation | Low motivatino reduces productivity | Schedule work effectively | 3 | 3 | 9
[7 empty] | Data corruption | Data could be lost or become corrupt | Use a recent git backup | 1 | 1 | 1
[7 empty] | Merge Conflicts | Merge conflicts could cause issues | Effective communication | 3 | 2 | 6
[7 empty] | Communication Failure | Poor communicatioin cause more issues | Effective communication | 1 | 3 | 3
[7 empty] | Group conflict | People could fall out | Pull your weight and be friendly | 2 | 3 | 6